## Milestones
Milestones | Milestone expectations | Due Date
Milestone 1 | a. Recognition of the UI pages, components, data model and folder structure for the project. | 2017-12-05
b. Creation of folder structure, data model, skeleton components, services.
Milestone 2 | Completion of 40% of features. | 2017-12-12
Milestone 3 | Completion of 80% of features. | 2017-12-19
Milestone 4 | a. Completion of registration and authentication features (completes the project 100%) | 2017-12-26
b. Submission of the implementation which includes: 1. Code checkin into wipro gitlab into the capstone folder. 2. Implementation Overview presentation(ppt) 3. Screen capture of the demo with audio description(How to run your application, demo of various features, codewalkthrough)
Milestone 5 | Evaluation by SME through live demo by the team. | 2018-01-05